## Sheet1
SL# | TASK |  | ORIGINAL ESTIMATION | REMAINING ESTIMATION | Assigne | Reporter | Type of the task | Summary of Ticket | Dropdown Component | Priority of Ticket | Due Date | Fix Version | Environment | Description | Attachment
|  | SUB TASKS | (In Hours) | (In Hours) | [6 empty] | Project starts 11/6
T1 | Database design |  | 16 | 5 | Cansu Salkıç | Rajesh Ghosh | Epic | Design and implemente the database for the project |  | Very High | 2017-11-08 | 1 | 0.1
T2 | Test server configaration (Local Share server) |  | 5 | 2 | José Pedro Teles | Rajesh Ghosh | Exception | Configurat the server to implement |  | Very High | 2017-11-06 | 1 | 0.2
T3 | Preparing Deployment Environment |  | 4 | 0 | José Pedro Teles | Rajesh Ghosh | Improvement | Set the enviroment for people to work |  | Very High | 2017-11-07 | 1 | 0.3
T4
T5 | Home page | Navbar | 6 | 4 | Rajesh Ghosh | Rajesh Ghosh | Improvement | Login, logout, company logo, filter, categories |  | Very High | 2017-11-07 | 1 | 0.3 | Web page were a user can see a log in option, the company logo, a filter option and categories from the shop
T6 |  | Product Slider | 8 | 2 | Rajesh Ghosh | Rajesh Ghosh | Improvement | Define Relevant Products and show each one of them after a period of time |  | Medium | 2017-11-14 | 1 | 0.3 | Rectangle in the middle of the page that displays information about featured products
T7 |  | Blog section | 5 | 1 | Rajesh Ghosh | Rajesh Ghosh | Improvement | Part of the Home page where people can comment and ask help to buy products |  | Low | 2017-11-15 | 1 | 0.3
|  | Footer | 5 | 2 | Rajesh Ghosh | Rajesh Ghosh | Bugs | Categories as contact us, sitemap |  | High | 2017-11-09 | 1 | 0.3
T9
T10 | Product Page | Filtering Option / Serach Product | 12 | 15 | Marina Camilo | José Pedro Teles | Improvement | Full Text Search Database Products |  | Medium | 2017-11-09 | 1 | 0.3
T11 |  | Top Selling Produc Slider | 5 | 5 | Marina Camilo | Victor Padi | Exception | Top Selling Products carousel |  | Medium | 2017-11-10 | 1 | 0.3
T12 |  | Product Category Section | 8 | 8 | Marina Camilo | Victor Padi | Task | Products' miniatures, adjusted by the page dimensions |  | Medium | 2017-11-13 | 1 | 0.3
T13
T14 | About Product Page | Product Descriptoin Section | 4 | 4 | Victor Padi | Victor Padi | Task | Section where people can get more info about the product. How is it works? When is it recommend? How should be used? Components and benefits |  | High | 2017-11-09 | 1 | 0.3
T15 |  | Buying Option / Add to cart section | 8 | 8 | Victor Padi | Victor Padi | Task | Make sure that when you open a new page the cart is the same. If anyone is log in, it keeps the card until the user drops it. Make sure that when a product is selected is on the shopping card section. It has to be possible to change the quantity of a product |  | Very High | 2017-11-08 | 1 | 0.3
T16 |  | Checkout and payment page | 3 | 3 | Victor Padi | Victor Padi | Bugs | Get the total cost of the items of the cart in different coins. Confirm Deliver adress. Check the payment method. |  | Very High | 2017-11-09 | 1 | 0.3
T18 | Blog page |  | 8 | 8 | Victor Padi | Cansu Salkıç | Improvement | Do a comment, change and delete user's loged in comments. See comments from other users, comment others users posts, give reactions to others user posts. |  | Low | 2017-11-16 | 1 | 0.3
T20 | Events page |  | 8 | 8 | José Pedro Teles | Cansu Salkıç | Task | Creat, update and delete admin's events. See next evets. |  | Low | 2017-11-14 | 1 | 0.3
T21 | Ecommerce Features | Inventory Management | 16 | 16 | Cansu Salkıç | Rajesh Ghosh | Task | Check stock in the store. Know the last bought products and their destiny. See statics of the goods sold. Control the stock requests. Annswer the question of the clients |  | Very High | 2017-11-10 | 1 | 0.3
T22 |  | Payment Getway integration | 16 | 16 | José Pedro Teles | Rajesh Ghosh | Improvement | Conect to the payment portal. Check when the payment is done in the portal. |  | Very High | 2017-11-09 | 1 | 0.3
T23 |  | Confirmation and Shipment | 5 | 5 | Marina Camilo | Cansu Salkıç | Task | Update the status order. |  | Very High | 2017-11-07 | 1 | 0.3
T24 |  | Coupons and offers implementation | 8 | 8 | Rajesh Ghosh | Cansu Salkıç | Task | Generate unique numbers of coupons. Create a section to receive any coupon or offer. Check the validation of the coupon/offer |  | Low | 2017-11-15 | 1 | 0.3
T25
T26 | Admin Panel | Admin Login and Registration | 8 | 8 | Rajesh Ghosh | Rajesh Ghosh | Bugs | Login should be visible during the site movimentation. Form for registration with name, last name, email and password. Add to the database the ew user. |  | High | 2017-11-13 | 1 | 0.3
T27 |  | Product Upload implementation | 11 | 11 | Victor Padi | Rajesh Ghosh | Bugs | Form with description, image, cost, and extra information sections. Add to the database the new poduct. It should be visible to users after filling the form |  | Medium | 2017-11-13 | 1 | 0.3
T28 |  | Offer and product update | 5 | 5 | Victor Padi | Rajesh Ghosh | Bugs | Form with description, image, cost, and extra information sections. Update the database about the existing poduct. It should be visible to users after filling the form. |  | Medium | 2017-11-14 | 1 | 0.3
T29 |  | Admin Logout | 3 | 3 | Victor Padi | Cansu Salkıç | Task | After closing the browser or click a botton, the admin account should be unacessible |  | Low | 2017-11-16 | 1 | 0.3
T30
T31
T32 | User Page
T33 |  | User Login and Logout | 4 | 4 | José Pedro Teles | Marina Camilo | Task | Login should be visible during the site movimentation. Ater click the logout botton or close the browser the user account should be unacessible |  | High | 2017-11-10 | 1 | 0.3
T34 |  | User Registration | 6 | 6 | José Pedro Teles | Marina Camilo | Task | Form for reistration with name last name, email and password. Add to the database the ew user. |  | High | 2017-11-13 | 1 | 0.3
T35 |  | Report Problem System | 4 | 4 | José Pedro Teles | Marina Camilo | Task | Form with type of question, and a descrition section. When submited it should be attached the client ID and the name of the user. |  | Low | 2017-11-15 | 1 | 0.3
T36 |  | Set Profile | 8 | 8 | Cansu Salkıç | José Pedro Teles | Improvement | Add a image to the account. Also, define the addres of the user |  | Medium | 2017-11-13 | 1 | 0.3
T37 |  | Update Profile | 4 | 4 | Cansu Salkıç | José Pedro Teles | Improvement | Form whereit should be possible to change the password, adress and image |  | Medium | 2017-11-14 | 1 | 0.3
T38 |  | My Orders Section | 3 | 3 | Cansu Salkıç | Cansu Salkıç | Task | List the orders that the user already had |  | Medium | 2017-11-15 | 1 | 0.3
T39 |  | Description of Order Section | 3 | 3 | Cansu Salkıç | José Pedro Teles | Improvement | Show the product list of the order that user seected |  | Medium | 2017-11-15 | 1 | 0.3
T40
T41 | Contact Us Page
T42 |  | Form to send message Section | 5 | 5 | Rajesh Ghosh | José Pedro Teles | Improvement | Form with name, email, and description area. |  | Low | 2017-11-16 | 1 | 0.3
T43 |  | Formal contacts Section with map | 4 | 4 | Rajesh Ghosh | José Pedro Teles | Task | Map with the address of the store. Email and phone of the store |  | Very High | 2017-11-08 | 1 | 0.3
T44
T45 | Testing and fix some bugs | Testing Shopping Cart | 6 | 6 | Marina Camilo | Marina Camilo | Testing | Test if we the product selected is in the shopping cart. Check if the shopping cart is the same when I log in in a different enviroment |  | High | 2017-11-14 | 1 | 0.3
T46 |  | Search Form, Sorting, Filtering, Pagination | 8 | 8 | Marina Camilo | Marina Camilo | Testing | Test if the Full Text Searching is working as it should be |  | Medium | 2017-11-15 | 1 | 0.3
T47 |  | Create account and Login Test | 6 | 6 | Victor Padi | José Pedro Teles | Testing | Create account, and see if it is succefully loged in. Also check if we restart the browser we need to log in again |  | High | 2017-11-16 | 1 | 0.3
T48 |  | Payments | 3 | 3 | Rajesh Ghosh | José Pedro Teles | Testing | Check if the payment section knows if the payment is already done |  | High | 2017-11-14 | 1 | 0.3
T49 |  | Post Purchase Test | 4 | 4 | Marina Camilo | Victor Padi | Testing | Check if user can purchase products. |  | Medium | 2017-11-15 | 1 | 0.3
T50 | Go Live / Deployment |  | 4 | 4 | José Pedro Teles | Victor Padi | Epic | Prepare server to receive a bigger amount of requests and lauch a version of the product |  | Very High | 2017-11-17 | 1 | 0.3
Total Time:
| Tasks # |  | 17D + 113H
| 38 |  | 113H =
17.3846
113 =
~18D
|  | Estimated time for 5 people: | 7

## Dashboard
Time to Finish: | 249 | H
Reporter
José Pedro Teles | 8
Victor Padi | 7
Cansu Salkıç | 6
Rajesh Ghosh | 12
Marina Camilo | 5
Assigne
| No. of Tasks | Hours
José Pedro Teles | 8 | 51
Victor Padi | 8 | 48
Cansu Salkıç | 6 | 50
Rajesh Ghosh | 9 | 52
Marina Camilo | 7 | 48
Type of Tasks
Bugs | 5
Exception | 2
Improvement | 11
Task | 13