## Main Sheet
SL# | TASK |  | ORIGINAL ESTIMATION | REMAINING ESTIMATION | Assigne | Reporter | Type of the task | Summary of Ticket | Dropdown Component | Priority of Ticket | Due Date | Fix Version | Environment | Description | Attachment | Q&A (Time) | Assigne
|  | SUB TASKS | (In Hours) | (In Hours) | [6 empty] | Project starts 11/6 |  |  |  |  | In Hour
T1 | Database design |  | 16 | 5 | Cansu Salkıç | Rajesh Ghosh | Epic | Design and implemente the database for the project | Data Base | Very High | 2017-11-08 | 1.0.0.0 | Production |  |  |  | Person 1
T2 | Test server configaration (Local Share server) |  | 5 | 2 | José Pedro Teles | Rajesh Ghosh | Exception | Test Local server | Backend | Very High | 2017-11-06 | 1.0.0.0 | Testing | 1. Test local server |  |  | Person 2
T3 | Preparing Deployment Environment |  | 4 | 0 | José Pedro Teles | Rajesh Ghosh | Improvement | Prepare Deployment Environment | Backend | Very High | 2017-11-07 | 1.0.0.0 | Deployment | 1.prepare deployment environment |  |  | Person 1
T4
T5 | Home page | Navbar | 6 | 4 | Rajesh Ghosh | Rajesh Ghosh | Improvement | Login, logout, company logo, filter, categories | Home Page,Data Base | Very High | 2017-11-07 | 1.0.0.0 | Production | 1. Login botton 2. Logout botton only apears after user login and end session when cliked returning to show only log in botton 3. Put the company logo image 4. Create a box to write and connect it to database to research for the best suitable products 5. Define the categories of the products and the website and order it. The sub categories should be showned when pass the mouse throw the categories name. |  |  | Person 1
T6 |  | Product Slider | 8 | 2 | Rajesh Ghosh | Rajesh Ghosh | Improvement | Define Relevant Products and show each one of them after a period of time | Home Page,Data Base | Medium | 2017-11-14 | 1.0.0.0 | Production | 1. Do a caroussel with boutstrap. 2. Connect to data base andcheck the products that are most relevant of the season. 3. Afterwards when the image passes, if clicked on the image get to the product page of the product that s displayed on the image |  |  | Person 2
T7 |  | Blog section | 5 | 1 | Rajesh Ghosh | Rajesh Ghosh | Improvement | Part of the Home page where people can comment and ask help to buy products | Home Page,Blog Page | Low | 2017-11-15 | 1.0.0.0 | Stage | 1. Define a block in the left side of the website 2. Add a botton to create edit and delet post. The edit and delete botton shoul work only if post done by user is selected. |  |  | Person 1
|  | Footer | 5 | 2 | Rajesh Ghosh | Rajesh Ghosh | Bug | Categories as contact us, sitemap | Home Page | High | 2017-11-09 | 1.0.0.0 | Production | 1. Define the design of the area of the footer (end of the page rectangle) 2. Define the categories and link them with the correct pages 3. Define the contact us contact and link the sitemap option. |  |  | Person 1
T9
T10 | Product Page | Filtering Option / Serach Product | 12 | 15 | Marina Camilo | José Pedro Teles | Improvement | Full Text Search Database Products | Home Page,Blog Page | Medium | 2017-11-09 | 1.0.0.0 | Production | 1. Define box to write on 2. Connect to database to search the input given by the user 3. Link to other page to how the result of search |  |  | Person 1
T11 |  | Top Selling Produc Slider | 5 | 5 | Marina Camilo | Victor Padi | Exception | Top Selling Products carousel | Produtos Page,Data Base | Medium | 2017-11-10 | 1.0.0.0 | Production | 1. Do a caroussel with boutstrap. 2. Connect to data base and check the products that sells more. 3. Afterwards when the image passes, if clicked on the image get to the product page of the product that s displayed on the image |  |  | Person 2
T12 |  | Product Category Section | 8 | 8 | Marina Camilo | Victor Padi | Task | Products' miniatures, adjusted by the page dimensions | Produtos Page,Data Base | Medium | 2017-11-13 | 1.0.0.0 | Production | 1. Do template for the page 2. Connect to database and get products 3. Be sure that when the windows is smaller are less products per line |  |  | Person 1
T13
T14 | About Product Page | Product Descriptoin Section | 4 | 4 | Victor Padi | Victor Padi | Task | Section where people can get more info about the product. How is it works? When is it recommend? How should be used? Components and benefits | Produtos Page,Data Base | High | 2017-11-09 | 1.0.0.0 | Production | 1. Define box to put text and photo 2. Connect to the databas to get the product photo. If don't has a photo get the photo of product image non available 3. Connect to the data base to get name the description and further reading if it has. If something i missing leave it blank |  |  | Person 2
T15 |  | Buying Option / Add to cart section | 8 | 8 | Victor Padi | Victor Padi | Task | Make sure that when you open a new page the cart is the same. If anyone is log in, it keeps the card until the user drops it. Make sure that when a product is selected is on the shopping card section. It has to be possible to change the quantity of a product | Home Page,Blog Page | Very High | 2017-11-08 | 1.0.0.0 | Production | 1. Define section to put the price and botton to add and substract to shopping cart 2. Connect to the database to get price 3. Check if when you click on the add botton adds one unit of that product to the cart 4. Check that when you click on the substract botton it will take out one unit of that product of the shopping cart. If the amunt of that product is 0 on the shopping cart shouldn't do anything |  |  | Person 2
T16 |  | Checkout and payment page | 3 | 3 | Victor Padi | Victor Padi | Bug | Get the total cost of the items of the cart in different coins. Confirm Deliver adress. Check the payment method. | Product Page,Shopping | Very High | 2017-11-09 | 1.0.0.0 | Production | 1. Define section for address confimation/edit. 2.Define section for list the items that the user is going to buy with box to edit the quantities and delete botton. 3. Define section with total value of purchase 4. Define section to choose the payment method |  |  | Person 2
T18 | Blog page |  | 8 | 8 | Victor Padi | Cansu Salkıç | Improvement | Do a comment, change and delete user's loged in comments. See comments from other users, comment others users posts, give reactions to others user posts. | Blog Page,Data Base | Low | 2017-11-16 | 1.0.0.0 | Production | 1. Define section with blog posts. 2. Connect to the database and get blog posts 3. Add bottons to edit, add and delete posts. 4. Add section in the blog posts to add comment 5. Add section to click and give reaction to posts |  |  | Person 1
Person 1
T20 | Events page |  | 8 | 8 | José Pedro Teles | Cansu Salkıç | Task | Creat, update and delete admin's events. See next evets. | Events Page,Data Base | Low | 2017-11-14 | 1.0.0.0 | Production | 1. Define section to upload image and content of event. 2. Define botton to update after you creat event 3. Define botton to delete event. 4. Define botton to see next event |  |  | Person 1
T21 | Ecommerce Features | Inventory Management | 16 | 16 | Cansu Salkıç | Rajesh Ghosh | Task | Check stock in the store. Know the last bought products and their destiny. See statics of the goods sold. Control the stock requests. Annswer the question of the clients | Backend | Very High | 2017-11-10 | 1.0.0.0 | Production | 1. Define section where i listed the products of the stores with the quantities. 2. Define section to visualize products purchased 3. Define section to see graphs of the products analisys 4. Define section where you send requests to get more products 5. Define section where you see clients' contact |  |  | Person 1
T22 |  | Payment Gateway integration | 16 | 16 | José Pedro Teles | Rajesh Ghosh | Epic | Conect to the payment portal. Check when the payment is done in the portal. | Backend,Shopping | Very High | 2017-11-09 |  | Production | 1. Link the payment to the payment portal 2. Analyse when the payment portal is closed and chek if the transaction was done. |  |  | Person 2
T23 |  | Confirmation and Shipment | 5 | 5 | Marina Camilo | Cansu Salkıç | Task | Update the status order. | Backend,Shopping | Very High | 2017-11-07 | 1.0.0.0 | Production | 1. Define botton on the clients purchase list to give feedback to the client of the state of the process |  |  | Person 1
T24 |  | Coupons and offers implementation | 8 | 8 | Rajesh Ghosh | Cansu Salkıç | Task | Generate unique numbers of coupons. Create a section to receive any coupon or offer. Check the validation of the coupon/offer | Backend | Low | 2017-11-15 | 1.0.0.0 | Stage | 1. Create a coupons genarete 2. Define quantity or users that can use the coupon 3. After get the coupon refresh automatically the changes |  |  | Person 2
T25
T26 | Admin Panel | Admin Login and Registration | 8 | 8 | Rajesh Ghosh | Rajesh Ghosh | Task | Login should be visible during the site movimentation. Form for registration with name, last name, email and password. Add to the database the ew user. | Admin,Data Base | High | 2017-11-13 | 1.0.0.0 | Production | 1. Define section where are going to put the username and password 2. Define botton for log in 3. Define botton for recover password 4. Define botton to register 5. Define section to put th email and password and confirm password, first name and last name |  |  | Person 1
T27 |  | Product Upload implementation | 11 | 11 | Victor Padi | Rajesh Ghosh | Task | Form with description, image, cost, and extra information sections. Add to the database the new poduct. It should be visible to users after filling the form | Admin,Data Base | Medium | 2017-11-13 | 1.0.0.0 | Production | 1. Define section to upload image of product, descrition, name of product and price. 2. Define botton to creat product |  |  | Person 2
T28 |  | Offer and product update | 5 | 5 | Victor Padi | Rajesh Ghosh | Task | Form with description, image, cost, and extra information sections. Update the database about the existing poduct. It should be visible to users after filling the form. | Admin,Data Base | Medium | 2017-11-14 | 1.0.0.0 | Production | 1. Define section to upload image of product, descrition, name of product and price. 2. Define botton to update product 3. Define botton to delete product |  |  | Person 2
T29 |  | Admin Logout | 3 | 3 | Victor Padi | Cansu Salkıç | Task | After closing the browser or click a botton, the admin account should be unacessible | Admin | Low | 2017-11-16 | 1.0.0.0 | Stage | 1. After clicking on the log out nav bar botton link to the first page |  |  | Person 2
T30
T31
T32 | User Page | [15 empty] | Person 1
T33 |  | User Login and Logout | 4 | 4 | José Pedro Teles | Marina Camilo | Task | Login should be visible during the site movimentation. Ater click the logout botton or close the browser the user account should be unacessible | User,Data Base | High | 2017-11-10 | 1.0.0.0 | Production | 1. Define section where are going to put the username and password 2. Define botton for log in 3. Define botton for recover password 4. End session after click logout |  |  | Person 1
T34 |  | User Registration | 6 | 6 | José Pedro Teles | Marina Camilo | Task | Form for reistration with name last name, email and password. Add to the database the ew user. | User,Data Base | High | 2017-11-13 | 1.0.0.0 | Production | 1. Define botton to register 2. Define section to put the email first name, last name and password and confirm password |  |  | Person 2
T35 |  | Report Problem System | 4 | 4 | José Pedro Teles | Marina Camilo | Task | Form with type of question, and a descrition section. When submited it should be attached the client ID and the name of the user. | User,Shopping | Low | 2017-11-15 | 1.0.0.0 | Stage | 1. Define section where usr could write 2. Define botton o submit and link it to the box of the company 3. Attach the Client ID and the name of the user |  |  | Person 1
T36 |  | Set Profile | 8 | 8 | Cansu Salkıç | José Pedro Teles | Improvement | Add a image to the account. Also, define the addres of the user | User,Data Base | Medium | 2017-11-13 | 1.0.0.0 | Stage | 1. Define section to upload photo 2. Define section to add address 3. Define button to save information |  |  | Person 1
T37 |  | Update Profile | 4 | 4 | Cansu Salkıç | José Pedro Teles | Improvement | Form whereit should be possible to change the password, adress and image | User,Data Base | Medium | 2017-11-14 | 1.0.0.0 | Stage | 1. Define section to upload photo 2. Define section to edit first name, last name, address, email, password 3. The precivous informations should be visible 4. Add botton to sav information |  |  | Person 2
T38 |  | My Orders Section | 3 | 3 | Cansu Salkıç | Cansu Salkıç | Task | List the orders that the user already had | User,Data Base,Shopping | Medium | 2017-11-15 | 1.0.0.0 | Stage | 1. Define section to show the list of the order 2. Each item should represented an order and should have the number of order and description with the titles of the products |  |  | Person 2
T39 |  | Description of Order Section | 3 | 3 | Cansu Salkıç | José Pedro Teles | Improvement | Show the product list of the order that user seected | User,Data Base,Shopping | Medium | 2017-11-15 | 1.0.0.0 | Stage | 1. Define section to list the items of the order 2. Each item should have the name of the product, descrition, photo and value 3. Each item should be linked with the product page of the product |  |  | Person 1
T40 | [16 empty] | Person 1
T41 | Contact Us Page | [15 empty] | Person 2
T42 |  | Form to send message Section | 5 | 5 | Rajesh Ghosh | José Pedro Teles | Improvement | Form with name, email, and description area. | Contact Us | Low | 2017-11-16 | 1.0.0.0 | Stage | 1. Define section to put name, email and a box to put the text. 2. Define boton to send message |  |  | Person 2
T43 |  | Formal contacts Section with map | 4 | 4 | Rajesh Ghosh | José Pedro Teles | Task | Map with the address of the store. Email and phone of the store | Contact Us | Very High | 2017-11-08 | 1.0.0.0 | Production | 1. Define ection with google map that has the location of the office. 2. Define a botton to link to the google maps page that has the location defined 3. Define a section where is the formal contacts of the store (email and phone) |  |  | Person 1
T44
T49 |  | Post Purchase Test | 4 | 4 | Marina Camilo | Victor Padi | Testing | Check if user can purchase products. | Backend,Shopping | Medium | 2017-11-15 | 1.0.0.0 | Testing | 1. After purchse, should be visible in order section the purchase information |  |  | Person 1
T50 | Go Live / Deployment |  | 4 | 4 | José Pedro Teles | Victor Padi | Epic | Prepare server to receive a bigger amount of requests and lauch a version of the product | Deployment | Very High | 2017-11-17 | 1.0.0.0 | Deployment | 1. Should go live and configure the system |  |  | Person 2
Total Time:
| Tasks # |  | 226 | H
| 38 |  | Total days:
34.7692
Estimated time for 5 people:

## TeamCapacity-1
Resourcing Plan |  | Days | Net Days |  | Capacity | Estimates | Diff.
Start Date for development | 2017-11-06 |  |  | Dev Team | 39 | 35 | 4
End date (code complete) | 2017-11-28 | 22 | 17 | Q&A Team |  | 15 | -15
Begin Regression Date
Gold version
Production release date
Dev Days in period | 22
Supported/unexpected | 0
Holidays | 2
R&D projects | 0.05

## TeamCap-2
Name | Team | Holidays | Off | Support Unexpected | R&D | Productivity Factor | Extra hours | Raw Work Days | Dev Days
Cansu Salkıç | ITM | 2 | 2 | 0 | 0.85 | 65 |  | 12.15 | 7.8975
José Pedro Teles | ITM | 2 | 4 | 0 | 0.85 | 65 |  | 10.15 | 6.5975
Rajesh Ghosh | ITM | 2 | 1 | 0 | 0.85 | 100 |  | 13.15 | 13.15
Marina Camilo | ITM | 2 | 2 | 0 | 0.85 | 30 |  | 12.15 | 3.645
Victor Padi | ITM | 2 | 3 | 0 | 0.85 | 65 |  | 11.15 | 7.2475
total: |  | 10 | 12 |  |  |  |  | 58.75 | 38.5375
Name | Team | Holidays | Off | Support Unexpected | R&D | Productivity Factor | Extra hours | Raw Work Days | Dev Days
Person 1 | ITM | 2 | 2 | 0 | 0.85 | 65 |  | 12.15 | 7.8975
Person 2 | ITM | 2 | 4 | 0 | 0.85 | 65 |  | 10.15 | 6.5975
total: |  | 4 | 6 |  |  |  |  | 22.3 | 14.495

## HolidaysCal
Name | Team | Total Holidays
Cansu Salkıç | ITM | 0
José Pedro Teles | ITM | 0
Rajesh Ghosh | ITM | 2
Marina Camilo | ITM | 0
Victor Padi | ITM | 0
Person 1 | ITM | 0
Person 2 | ITM | 0
Date | Cansu Salkıç | José Pedro Teles | Rajesh Ghosh | Marina Camilo | Victor Padi | Person 1 | Person 2
2017-11-06
2017-11-07
2017-11-08
2017-11-09
2017-11-10
2017-11-11
2017-11-12
2017-11-13
2017-11-14
2017-11-15
2017-11-16
2017-11-17
2017-11-18
2017-11-19
2017-11-20 |  |  | 1
2017-11-21
2017-11-22
2017-11-23
2017-11-24
2017-11-25
2017-11-26
2017-11-27
2017-11-28 |  |  | 1

## Dropdown Lists
Dev Members: | Type of the Task: | Type of Component: | Type of Priority: | Fix Version: | Environment: | Test Members:
Cansu Salkıç | Bug | Data Base | Very High | 1.0.0.0 | Production | Person 1
José Pedro Teles | Improvement | Backend | High |  | Deployment | Person 2
Rajesh Ghosh | Epic | Backend,Shopping | Medium |  | Testing
Marina Camilo | Testing | Home Page | Low |  | Stage
Victor Padi | UI | Home Page,Data Base
| Exception | Home Page,Blog Page
| Data Issue | Producs Page
| Task | Produtos Page,Data Base
Product Page,Shopping
Blog Page,Data Base
Events Page,Data Base
Admin,Data Base
Admin
Admin,User
User,Data Base
User,Shopping
User,Data Base,Shopping
Contact Us
Shopping
Deployment

## Dashboard
Time to Finish: | 226 | H
Reporter
José Pedro Teles | 6
Victor Padi | 7
Cansu Salkıç | 6
Rajesh Ghosh | 12
Marina Camilo | 3
Assigne
| No. of Tasks | Hours
José Pedro Teles | 8 | 51
Victor Padi | 7 | 42
Cansu Salkıç | 6 | 50
Rajesh Ghosh | 8 | 49
Marina Camilo | 5 | 34
Type of Tasks
Bugs | 0
Exception | 2
Improvement | 10
Task | 16