## Sheet1
SL# | TASK |  | ORIGINAL ESTIMATION | REMAINING ESTIMATION | Assigne | Reporter | Type of the task
|  | SUB TASKS | (In Hours) | (In Hours)
T1 | Database design |  | 16 | 5 | Cansu Salkıç | Rajesh Ghosh | Bugs
T2 | Test server configaration (Local Share server) |  | 5 | 2 | José Pedro Teles | Rajesh Ghosh | Exception
T3 | Preparing Deployment Environment |  | 4 | 0 | José Pedro Teles | Rajesh Ghosh | Improvement
T4
T5 | Home page | Navbar | 6 | 4 | Rajesh Ghosh | Rajesh Ghosh | Improvement
T6 |  | Product Slider | 8 | 2 | Rajesh Ghosh | Rajesh Ghosh | Improvement
T7 |  | Blog section | 5 | 1 | Rajesh Ghosh | Rajesh Ghosh | Improvement
|  | Footer | 5 | 2 | Rajesh Ghosh | Rajesh Ghosh | Bugs
T9
T10 | Product Page | Filtering Option / Serach Product | 12 | 15 | Marina Camilo | José Pedro Teles | Improvement
T11 |  | Top Selling Produc Slider | 5 | 5 | Marina Camilo | Victor Padi | Exception
T12 |  | Product Category Section | 8 | 8 | Marina Camilo | Victor Padi | Task
T13
T14 | About Product Page | Product Descriptoin Section | 4 | 4 | Victor Padi | Victor Padi | Task
T15 |  | Buying Option / Add to cart section | 8 | 8 | Victor Padi | Victor Padi | Task
T16 |  | Checkout and payment page | 3 | 3 | Victor Padi | Victor Padi | Bugs
T18 | Blog page |  | 8 | 8 | Victor Padi | Cansu Salkıç | Improvement
T20 | Events page |  | 8 | 8 | José Pedro Teles | Cansu Salkıç | Task
T21 | Ecommerce Features | Inventory Management | 16 | 16 | Cansu Salkıç | Rajesh Ghosh | Task
T22 |  | Payment Getway integration | 16 | 16 | José Pedro Teles | Rajesh Ghosh | Improvement
T23 |  | Confirmation and Shipment | 5 | 5 | Marina Camilo | Cansu Salkıç | Task
T24 |  | Coupons and offers implementation | 8 | 8 | Rajesh Ghosh | Cansu Salkıç | Task
T25
T26 | Admin Panel | Admin Login and Registration | 8 | 8 | Rajesh Ghosh | Rajesh Ghosh | Bugs
T27 |  | Product Upload implementation | 11 | 11 | Victor Padi | Rajesh Ghosh | Bugs
T28 |  | Offer and product update | 5 | 5 | Victor Padi | Rajesh Ghosh | Bugs
T29 |  | Admin Logout | 3 | 3 | Victor Padi | Cansu Salkıç | Task
T30
T31
T32 | User Page
T33 |  | User Login and Logout | 4 | 4 | José Pedro Teles | Marina Camilo | Task
T34 |  | User Registration | 6 | 6 | José Pedro Teles | Marina Camilo | Task
T35 |  | Report Problem System | 4 | 4 | José Pedro Teles | Marina Camilo | Task
T36 |  | Set Profile | 8 | 8 | Cansu Salkıç | José Pedro Teles | Improvement
T37 |  | Update Profile | 4 | 4 | Cansu Salkıç | José Pedro Teles | Improvement
T38 |  | My Orders Section | 3 | 3 | Cansu Salkıç | Cansu Salkıç | Task
T39 |  | Description of Order Section | 3 | 3 | Cansu Salkıç | José Pedro Teles | Improvement
T40
T41 | Contact Us Page
T42 |  | Form to send message Section | 5 | 5 | Rajesh Ghosh | José Pedro Teles | Improvement
T43 |  | Formal contacts Section with map | 4 | 4 | Rajesh Ghosh | José Pedro Teles | Task
T44
T45 | Testing and fix some bugs | Testing Shopping Cart | 6 | 6 | Marina Camilo | Marina Camilo | Bugs
T46 |  | Search Form, Sorting, Filtering, Pagination | 8 | 8 | Marina Camilo | Marina Camilo | Bugs
T47 |  | Create account and Login Test | 6 | 6 | Victor Padi | José Pedro Teles | Bugs
T48 |  | Payments | 3 | 3 | Rajesh Ghosh | José Pedro Teles | Bugs
T49 |  | Post Purchase Test | 4 | 4 | Marina Camilo | Victor Padi | Bugs
T50 | Go Live / Deployment |  | 4 | 4 | José Pedro Teles | Victor Padi | Task
Total Time:
| Tasks # |  | 17D + 113H
| 38 |  | 113H =
17.3846
113 =
~18D
|  | Estimated time for 5 people: | 7

## Dashboard
Time to Finish: | 249 | H
Reporter
José Pedro Teles | 8
Victor Padi | 7
Cansu Salkıç | 6
Rajesh Ghosh | 12
Marina Camilo | 5
Assigne
| No. of Tasks | Hours
José Pedro Teles | 8 | 51
Victor Padi | 8 | 48
Cansu Salkıç | 6 | 50
Rajesh Ghosh | 9 | 52
Marina Camilo | 7 | 48
Type of Tasks
Bugs | 11
Exception | 2
Improvement | 11
Task | 14